## Tax Return Project Plan
Tax Return Project Plan
|  |  |  | October |  |  |  | November |  |  |  | December
Year ended 30 June 20XX |  |  |  | Week |  |  |  | Week |  |  |  | Week
TASK | PERSON RESPONSIBLE | START | END | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Return preparation process
Download the final Trial Balance, General Ledger and Fixed Asset Register. Ensure correct opening balances. | Junior Accountant | 2022-10-02 | 2022-10-03
Review General Ledger and ensure tax treatment. Use ‘Tax Issues Management Procedures’ to prepare the working files. | Senior Accountant | 2022-10-04 | 2022-10-31
Prepare, send and follow up income tax return queries from External Advisors. | Senior Accountant | 2022-11-01 | 2022-11-18
Finalise year-end Working File Draft Income Tax Returns and Schedules. | Senior Accountant | 2022-11-20 | 2022-12-07
Internal Review and Sign Off on Returns
Review Working File and draft Income Tax Returns and schedules | CFO | 2022-12-07 | 2022-12-17
Sign off and lodgement of returns (prior to Christmas). | Public Officer | 2022-12-17 | 2022-12-22